## Slide 1
Revised plan: hand-in 13 December
Two weeks per chapter, overlapping by one week. Chapter 5 is the core, so it gets three.
W40
28 Sep
W41
5 Oct
W42
12 Oct
W43
19 Oct
W44
26 Oct
W45
2 Nov
W46
9 Nov
W47
16 Nov
W48
23 Nov
W49
30 Nov
W50
7 Dec
Scope and outline
Ch. 2: literature review
Ch. 3: the Global Gas Model
Ch. 4: LLM agents
Ch. 5: where AI fits
Ch. 6–8: closing chapters
Introduction and abstract
Supervisor feedback, revise, hand in
Milestones: drafted by end of week
Outline
Ch. 2
Ch. 3
Ch. 4
Ch. 5
Full draft, 29 Nov
Hand-in, 13 Dec
The introduction is written last, once we know what the thesis actually says. Two weeks are kept for feedback and revision.